## Feature List
Feature | Benefit(s)
Website Login | Offers secure system login for the bank employees
Manage Customer Information | Facility for bank employees to quickly onboard a new customer, update customer details & closures
Manage Account details | A convenient and safe experience for opening a new bank account, maintaining the account & closures
Online search | Facility for bank employees to carry out online search on cuastomers and accounts
Operate Banking transactions | Facility for bank employees to carry out customer transactiuons

## Product Backlog
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initiial Size Estimate (SP) (Using numeric 1-10 scale) | Business Priority | Sprint Number | Comments
Website Home Page | US001 | As a customer-account executive /cashier / teller I want to be able to see the home page So that I can see the homepage of the website | Simply display a home page welcome screen | 2 | High | 1 | Finished goals as expected
Website Login | US002 | As a customer-account executive /cashier / teller I want to be able to log in the bank website with my user ID and password So that I carry out my transactions | * The log in page should be user id and password protected * The user ID can be alphabetic or alphanumeric and should have a minimum of 8 characters * Password should contain 10 characters including one special character, one upper case, one numeric. *Session Management should be done on Login and Logout. Note : Ref Fig1 – Screens_RetailBank_Casestudy.doc | 6 | high | 1 | Faced framework specific issues while using Monogengine as ORM
Manage Customer Information | US003 | As a customer-account executive I want to be able to capture new customer information So that I can create a new customer in the system | * Should be able to enter the values on the screen * Success or Error response should be displayed on the screen with user friendly messages Note : Ref Fig2 – Screens_RetailBank_Casestudy.doc | 3 | high | 1 | Finished goals as expected
| US004 | As a customer-account executive I want to be able to edit existing customer information So that I can store the updated customer information in the system | * Should be able to view the details before updating * Updates of Key customer info like SSN should not be permitted * Success or Error response should be displayed on the screen with user friendly messages Note : Ref Fig3 – Screens_RetailBank_Casestudy.doc | 4 | high | 1 | Restrictng the user fields were faced with edge case exception; was fixed
| US005 | As a customer-account executive I want to be able to delete existing customer from system | * Should be able to view the details before deleting * Success or Error response should be displayed on the screen with user friendly messages Note : Ref Fig4 – Screens_RetailBank_Casestudy.doc | 3 | high | 1 | Finished goals as expected
| US006 | As a customer-account executive I want to be able to view the status of all the customers of the bank | * Should be able to view the status of all the customers of the bank * Display records on the screen * Should be able to refresh and get the latest status of each customer Note : Ref Fig5 – Screens_RetailBank_Casestudy.doc | 5 | high | 1 | Deserializing the object and key nameing issues between front and backend was fixed
| US007 | As a customer-account executive I want to be able to view the details of all the customers of the bank | * Should be able to view the details of selected customer of the bank | 2 | high | 1 | Finished goal as expected
Manage Account Details | US008 | As a customer-account executive I want to be able to capture account details So that I can create a new bank account for an existing customer | * Should be able to create account for existing customer only * Should be able to create different types of accounts * Success or Error response should be displayed on the screen with user friendly messages Note : Ref Fig6 – Screens_RetailBank_Casestudy.doc | 6 | high | 1 | Went surprinsingly smooth since we expected to face issue with user authentication but was mitigated by adopting coding best practices
| US009 | As a customer-account executive I want to be able to delete an account of an existing customer | * Should be able to view the account details before deleting * Success or Error response should be displayed on the screen with user friendly messages Note : Ref Fig7 – Screens_RetailBank_Casestudy.doc | 4 | high | 1 | Finished goal as expected
| US0010 | As a customer-account executive I want to be able to view the status of all the accounts of the bank | * Should be able to view the status of all the accounts maintained in the bank * Should display all records in screen * Should be able to refresh and get the latest status of each account Note : Ref Fig8 – Screens_RetailBank_Casestudy.doc | 4 | high | 1 | Faced issues in coupling the redirect url with the passed value in display tables
Online Search | US011 | As a customer-account executive I want to be able to search for a customer So that I am able to view the details | * Should be able to search for the customer details using SSN ID or Customer Id * User friendly responses should be provided for both success & failure Note : Ref Fig9 – Screens_RetailBank_Casestudy.doc | 4 | high | 1 | Finished goal as expected
| US012 | As a Cashier/ Teller I want to be able to search for a bank account So that I am able to view the details | * Should be able to search for the account details using Account ID and Customer Id * User friendly responses should be provided for both success & failure Note : Ref Fig10 – Screens_RetailBank_Casestudy.doc | 5 | high | 1 | Finished goal as expected
Operate Banking Transactions | US013 | As a Cashier/ Teller I want to be able to deposit money into a customer's account So that I am able to service the customer's request | * Should be able to view the customer account details before initiating the transaction * Should display the latest account details after the transaction is completed * Should display user friendly 'Success' or 'Error' response Note : Ref Fig11 – Screens_RetailBank_Casestudy.doc | 7 | high | 1 | Finished goal as expected
| US014 | As a Cashier/ Teller I want to be able to withdraw money from a customer's account So that I am able to service the customer's request | * Should be able to view the customer account details before initiating the transaction * Should display the latest account details after the transaction is completed * Should display user friendly 'Success' or 'Error' response Note : Ref Fig12 – Screens_RetailBank_Casestudy.doc | 7 | high | 1 | Implemented case handling with withdraw amount greater than balance; update message was updated appropriately
| US015 | As a Cashier/ Teller I want to be able to transfer money from a customer's account So that I am able to service the customer's request | * Should be able to view the customer account details before initiating the transaction * Should display the latest account details after the transaction is completed * Should display user friendly 'Success' or 'Error' response Note : Ref Fig13 – Screens_RetailBank_Casestudy.doc | 8 | high | 1 | adhoc functions were created to handle the mixute of deposit and withdrawal actions along with verification of backend and frontend
| US016 | As a Cashier/ Teller I want to be able to print an account statement So that I am able to service the customer's request | * Should be able to choose the no of transactions to be displayed or Start date and End date * Should be able to view the statement online and to be able to get a physical copy * Should display user friendly 'Success' or 'Error' response Note : Ref Fig14.1, Fig14.2 – Screens_RetailBank_Casestudy.doc | 3 | high | 1 | Finished goal as expected