## Sprint 1
Sprint 1 Retrospective
The Good | Continue Doing
Adopting standard coding practices helped in mitigating issues with code maintainence
Regular fixed time virtual meetings helped in updating all the members
Using ORM mitigated the issues of DB connection pooling and threading errors
Version controlling using Git and efficient use of github
The Bad | Start Doing - Improvement items/ Agreements on new way of working
Stopped the use of 3rd party not well tested libraries after facing issues and expending time
Decoupling of DB with frontend has to be enforced not only for some but for all methods
Resuablitiy of code has to be enforced
The Ugly | Stop Doing
Lack of code reuseability
Reduce reliability on untested 3rd party libraries
Lack of proper time management