## Sprint 1 Backlog
Story # | Sprint Backlog Item | Task # | Volunteer | Task Details | Initial Effort Estimate (hrs) | New Estimates of Effort remaining at end of | [5 empty] | Status
[6 empty] | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
US001 | As a customer-account executive /cashier / teller I want to be able to see the home page So that I can see the homepage of the website | Task 1 | Kiran Chandra | Write a program for displaying the home page | 3 | 3 | 2 | 1 | 1 | 0 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI for the Home page | 5 | 3 | 3 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Design and create the DB fields | 5 | 3 | 3 | 0 | 0 | 2 | 0 | Closed
|  | Task 4 | Nishant Kumar | Check for corner/edge cases | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Closed
|  | Task 5 | Rahul Kumar Arya | Optimize UI for user | 2 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | Closed
|  | Task 6 | Shambhavi Shukla | Dry test run | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Closed
US002 | As a customer-account executive /cashier / teller I want to be able to log in the bank website with my user ID and password So that I carry out my transactions | Task 1 | Kiran Chandra | Write a program for verifying the login credentials | 5 | 4 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the login page with success or fail message | 5 | 3 | 3 | 1 | 1 | 0 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Design the backend logic for verification | 5 | 3 | 4 | 1 | 1 | 0 | 0 | Closed
|  | Task 4 | Nishant Kumar | Check for corner/edge cases | 3 | 0 | 0 | 0 | 1 | 0 | 0 | Closed
|  | Task 5 | Rahul Kumar Krya | Optimize UI for user | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 6 | Shambhavi Shukla | Dry test run | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Closed
US003 | As a customer-account executive I want to be able to capture new customer information So that I can create a new customer in the system | Task 1 | Kiran Chandra | Write a program to capture the data from HTML forms | 6 | 2 | 2 | 6 | 0 | 0 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI for capture data html form | 6 | 3 | 0.5 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Insert the data into Database | 5 | 3 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Nishant Kumar | check for corner/edge cases | 4 | 0 | 0 | 0 | 2 | 0 | 0 | Closed
|  | Task 5 | Rahul Kumar Krya | Optimize UI for user | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 6 | Shambhavi Shukla | Dry test run | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Closed
US004 | As a customer-account executive I want to be able to edit existing customer information So that I can store the updated customer information in the system | Task 1 | Kiran Chandra | Write program to get the data from HTML form | 5 | 4 | 1 | 1 | 0 | 0 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI for Update page | 5 | 5 | 1 | 1 | 0 | 0 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Update the appropriate fields in database | 5 | 4 | 2 | 2 | 1 | 0 | 0 | Closed
|  | Task 4 | Nishant Kumar | check for corner/edge cases | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Closed
|  | Task 5 | Rahul Kumar Krya | Optimize UI for user | 1.5 | 1 | 1 | 0 | 0 | 1 | 0 | Closed
|  | Task 6 | Shambhavi Shukla | Dry test run | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Closed
US005 | As a customer-account executive I want to be able to delete existing customer from system | Task 1 | Kiran Chandra | Write the program to get the data and verify the ID | 6 | 3 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI page for Delete view | 6 | 4 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Delete the entry and verify the deletion action | 6 | 3 | 3 | 2 | 0 | 0 | 0 | Closed
|  | Task 4 | Nishant Kumar | check for corner/edge cases | 2 | 0 | 0 | 0 | 0 | 1 | 0 | Closed
|  | Task 5 | Rahul Kumar Krya | Optimize UI for user | 0.5 | 1 | 1 | 0 | 0 | 1 | 0 | Closed
|  | Task 6 | Shambhavi Shukla | Dry test run | 0.5 | 0 | 0 | 0 | 0 | 1 | 0 | Closed
US006 | As a customer-account executive I want to be able to view the status of all the customers of the bank | Task 1 | Kiran Chandra | Verify the logged in user access privileges | 5 | 3 | 2 | 4 | 4 | 5 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI for displaying the details | 4.5 | 3 | 2 | 1 | 0 | 0 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Deserailize the DB fields for front end use | 4 | 3 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 4 | Nishant Kumar | check for corner/edge cases | 1 | 1 | 0 | 0 | 0 | 1 | 0 | Closed
|  | Task 5 | Rahul Kumar Krya | Optimize UI for user | 1 | 1 | 1 | 2 | 0 | 1 | 0 | Closed
|  | Task 6 | Shambhavi Shukla | Dry test run | 1 | 1 | 0 | 0 | 0 | 1 | 0 | Closed
US007 | As a customer-account executive I want to be able to capture account details So that I can create a new bank account for an existing customer | Task 1 | Kiran Chandra | Get the ID from front end and counter verify the ID | 4 | 4 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI for the Account creating page | 4 | 4 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Design and Create fields for Account Creation | 4 | 3 | 2 | 1 | 0 | 0 | 0 | Closed
|  | Task 4 | Nishant Kumar | check for corner/edge cases | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Closed
|  | Task 5 | Rahul Kumar Krya | Optimize UI for user | 2 | 0 | 0 | 0 | 0 | 1 | 0 | Closed
|  | Task 6 | Shambhavi Shukla | Dry test run | 1.5 | 0 | 0 | 0 | 0 | 1 | 0 | Closed
US008 | As a customer-account executive I want to be able to view the details of all the customers of the bank | Task 1 | Kiran Chandra | Write the program to verify user privileges | 4 | 3 | 2 | 2 | 1 | 0 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI to display all details | 4 | 4 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Get and deserialize the data for display | 5 | 3 | 2 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Nishant Kumar | Check for corner/edge cases | 1.5 | 1 | 1 | 0 | 0 | 0 | 0 | Closed
|  | Task 5 | Rahul Kumar Arya | Optimize UI for user | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 6 | Shambhavi Shukla | Dry test run | 0.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | Closed
US009 | As a customer-account executive I want to be able to delete an account of an existing customer | Task 1 | Kiran Chandra | Get the required data fields from UI | 5 | 4 | 2 | 2 | 1 | 0 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI for the customer delete page with appropriate fields | 5 | 3 | 3 | 1 | 0 | 0 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Get the correct account object from database | 5 | 3 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 4 | Nishant Kumar | check for corner/edge cases | 0.5 | 0 | 0 | 1 | 0 | 0 | 0 | Closed
|  | Task 5 | Rahul Kumar Krya | Optimize UI for user | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 6 | Shambhavi Shukla | Dry test run | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | Closed
US010 | As a customer-account executive I want to be able to view the status of all the accounts of the bank | Task 1 | Kiran Chandra | Write the privileges to check logged users | 4 | 4 | 2 | 1 | 0 | 0 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI for displaying the account details | 4 | 1 | 1 | 3 | 0 | 0 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Get and deserialize the data for display | 4 | 1 | 1 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Nishant Kumar | check for corner/edge cases | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Closed
|  | Task 5 | Rahul Kumar Krya | Optimize UI for user | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Closed
|  | Task 6 | Shambhavi Shukla | Dry test run | 1 | 0 | 0 | 0 | 0 | 1.5 | 0 | Closed
US011 | As a customer-account executive I want to be able to search for a customer So that I am able to view the details | Task 1 | Kiran Chandra | Get and verify the recieved ID from UI | 6 | 3 | 2 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI for GET and POST forms | 5 | 3 | 1 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Get and serialize the correct customer details | 5 | 3 | 1 | 1 | 0 | 0 | 0 | Closed
|  | Task 4 | Nishant Kumar | check for corner/edge cases | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 5 | Rahul Kumar Krya | Optimize UI for user | 1 | 3 | 2 | 4 | 4 | 5 | 0 | Closed
|  | Task 6 | Shambhavi Shukla | Dry test run | 1 | 3 | 4 | 4 | 4 | 2 | 0 | Closed
US012 | As a Cashier/ Teller I want to be able to search for a bank account So that I am able to view the details | Task 1 | Kiran Chandra | Get and verify the recieved ID from UI | 5 | 4 | 1 | 1 | 0 | 0 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI for GET and POST forms | 5 | 4 | 2 | 2 | 1 | 0 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Get and serialize the correct account details | 4.5 | 3 | 2 | 2 | 2 | 0 | 0 | Closed
|  | Task 4 | Nishant Kumar | check for corner/edge cases | 1 | 0 | 0 | 1 | 1 | 0 | 0 | Closed
|  | Task 5 | Rahul Kumar Krya | Optimize UI for user | 1 | 0 | 1 | 1 | 0 | 0 | 0 | Closed
|  | Task 6 | Shambhavi Shukla | Dry test run | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Closed
US013 | As a Cashier/ Teller I want to be able to deposit money into a customer's account So that I am able to service the customer's request | Task 1 | Kiran Chandra | Get and verify the recieved ID from UI for money deposit | 5 | 4 | 3 | 2 | 0 | 0 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI for the deposit page | 5 | 2 | 2 | 1 | 0.5 | 0 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Update the appropriate fields after deposit in DB | 5 | 3 | 3 | 1 | 1 | 2 | 0 | Closed
|  | Task 4 | Nishant Kumar | check for corner/edge cases | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Closed
|  | Task 5 | Rahul Kumar Krya | Optimize UI for user | 1 | 2 | 1 | 0 | 0 | 0 | 0 | Closed
|  | Task 6 | Shambhavi Shukla | Dry test run | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | Closed
US014 | As a Cashier/ Teller I want to be able to withdraw money from a customer's account So that I am able to service the customer's request | Task 1 | Kiran Chandra | Get the appropriate fields from UI and verify if Withdraw amount is correct | 3 | 2 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI for withdraw field with input restrictions | 3 | 6 | 5 | 5 | 2 | 2 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Update the fields after successful withdrawal | 3 | 5 | 3 | 3 | 1 | 0 | 0 | Closed
|  | Task 4 | Nishant Kumar | check for corner/edge cases | 0.5 | 1 | 0 | 0 | 0.5 | 0 | 0 | Closed
|  | Task 5 | Rahul Kumar Krya | Optimize UI for user | 1 | 2 | 0 | 0 | 2 | 0 | 0 | Closed
|  | Task 6 | Shambhavi Shukla | Dry test run | 1 | 1 | 1 | 0 | 1 | 0 | 0 | Closed
US015 | As a Cashier/ Teller I want to be able to transfer money from a customer's account So that I am able to service the customer's request | Task 1 | Kiran Chandra | Get the appropriate fields from UI and verify if Withdraw amount is correct | 4 | 4 | 4 | 0 | 3 | 3 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI for tranfer with restrictions | 4 | 3 | 3 | 1 | 1 | 1 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Update the fields after successful transfers | 4 | 3 | 3 | 2 | 2 | 1 | 0 | Closed
|  | Task 4 | Nishant Kumar | check for corner/edge cases | 0.5 | 4 | 4 | 2 | 2 | 0 | 0 | Closed
|  | Task 5 | Rahul Kumar Krya | Optimize UI for user | 0.5 | 1 | 0 | 1 | 1 | 0 | 0 | Closed
|  | Task 6 | Shambhavi Shukla | Dry test run | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | Closed
US016 | As a Cashier/ Teller I want to be able to print an account statement So that I am able to service the customer's request | Task 1 | Kiran Chandra | Verify the logged in user access privileges for accessing accounts and get the date range or ID | 3 | 2 | 2 | 1 | 0 | 0 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI for displaying the account statement by date range or ID | 3 | 3 | 2 | 2 | 1 | 0 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Get the accounts based on the data range or ID as passed and deserialize it. | 3 | 3 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 4 | Nishant Kumar | check for corner/edge cases | 0.5 | 0 | 0 | 0 | 1 | 0 | 0 | Closed
|  | Task 5 | Rahul Kumar Krya | Optimize UI for user | 0.5 | 1 | 0 | 0 | 0 | 1 | 0 | Closed
|  | Task 6 | Shambhavi Shukla | Dry test run | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | Closed
|  |  |  | Total | 278 | 186 | 118.5 | 87 | 44.5 | 42 | 0

## Sprint 1 Burndown Chart
Day0 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
278 | 186 | 118.5 | 87 | 44 | 42 | 0